## backlog
uid | Sprint | prio | Size | status | dep on | name | notes / blockers
BUG-001 | S01 | P1 | M | todo |  | 1d strip updated incorrectly | Long-standing; strip semantics still wrong in camera observation path.
BUG-002 | S01 | P1 | M | wip | FEAT-005 | Clouds not visibly moving in simulation | Formation generator exists (notebook 02); kinematic motion / render feedback still weak.
BUG-003 | S01 | P0 | S | wip |  | Integration tests out of sync with SimulationConfig / cloud precompute | movement_constraints e2e (controller_mode removed); cloud formation e2e; test_cloud_arc_precompute (2 red).
STR-001 |  | P2 | L | todo |  | Reduce mission/global constant coupling in training_runtime | Pass scenario/config explicitly instead of scraping MISSION globals.
STR-002 |  | P2 | M | todo |  | Simplify/rename env adapter API | Reflect non-Gym-physics behavior in naming and surface.
STR-003 |  | P3 | S | todo |  | Remove deprecated run_simulation compatibility args | After call sites migrated.
STR-004 | S01 | P1 | M | wip |  | Commit and split uncommitted WIP | ~3.5k LOC on feat/backend-stuff: notebooks/utils vs sim/render vs experiments vs cursor skills.
FEAT-001 | S01 | P1 | L | wip |  | Optimize simulation performance for fast ML iteration | C/D ray batch promoted; sim_timing in place; export still bottleneck (~82s vs ~10s sim).
FEAT-002 | S01 | P1 | S | todo | FEAT-001 | Promote video export frame_stride=2 | Experiment supported ~2x export speedup; not yet in production render path.
FEAT-003 |  | P3 | S | todo |  | Telemetry: environment avg cloud speed
FEAT-004 | S01 | P0 | M | wip | BUG-003 | Complete S01 notebook 03 - movement constraints | AttitudeSafetyController + unit tests green; e2e red; MP4 in artifacts/video_archive/. Plan: movement_constraints.plan.md
FEAT-005 | S01 | P0 | M | wip | BUG-003 | Complete S01 notebook 02 - clouds | cloud_formation + verification utils; sim integration test red; visible motion TBD.
FEAT-006 | S01 | P1 | XL | todo | FEAT-005 | clouds_and_target_grid plan (production) | Min observation time, stillness, area score, off-nadir damage, secondary FOV — .cursor/plans/v2/clouds_and_target_grid_808c8677.plan.md
DONE-001 | S01 | P2 | M | done |  | Sensor kernel: fused multi-camera ray batch (hypothesis C) | Promoted 2026-06-03; ~1.6x micro, ~1.18x episode.
DONE-002 | S01 | P2 | M | done |  | camera_2d: vectorized tensor cloud x ray hits (hypothesis D) | Promoted 2026-06-03; ~2.9x line kernel @ 63 clouds.
DONE-003 | S01 | P2 | S | done |  | sim_timing experiment harness | High-cloud profile baseline; backend/scripts/experiments/sim_timing/
DONE-004 | S01 | P2 | M | done |  | Attitude safety controller + ATTITUDE_SAFETY constants | Notebook 03 core logic; unit tests green.
STR-005 | S01 | P1 | M | todo |  | Strict JSON-driven simulation configuration loader / validator | Load simulation config from one JSON source and throw hard errors for ill-defined satellite, torque policy, and camera specs.
BUG-004 | S01 | P0 | M | todo |  | MPO agent spams take-picture; budget early-stop blocks learning | Notebook 08: agent fires shutter every step, exhausts capture budget, episode truncates early (early_stop_on_budget). Full-orbit rollouts never complete; learning signal collapsed. Fix: shutter action bias/exploration, reward for wasted shutters, action masking when budget low, or train-phase early-stop policy.